## Sheet1
PFM/EPFM
2023/24FY MANNEX PLAN
CORE
level 1 | Creating a solid foundation
Creating a continous improvement culture
creating stable and efficient process
Month
Quarter | Q1 | Building a solid foundation for processes and People | Q2 | Building a solid foundation + creating continous improvement culture | Q3 | Driving a Continous improvement Culture
| CORE | Activities | CORE | Activites | CORE | Activites
Action Plan | Daily Management | Align Leadership/leadership buy in ( inclusion of Mannex KPIs into objective setting | DaIly Management | Establish Tier 1 meeting using the categorized crew method | Daily Management | Mid year review of KPIs
|  | Review Tier 3 meetings to include closure tracking |  | Track and Monitor meetings for compliance. Shift caha |  | Performance Assessment of operation crew and reward/recognition
|  | Categorize shift operators into crews to monitor performance | Visual Management | Daily update of KPI status board |  | Group mannex assessment
|  | Introduction of KPI status board |  |  | Visual Mangement and
| 5S | Review and support 5S projects in different zones |  | Implement Oil level indicators, Process flow arrows guage labels
|  |  | 5S | Monthly 5s audits
| Visual Management | SOP/WI display
| Standardization | Review SOP gaps for all production activities | Process improvement | Monthly OSHIN analysis | Process improvement | Lean Projects
|  | check for compliance if SOP is being adhered to and fix discreprancies |  | BDA |  | Shrink Management/
| Process improvement | RCA training embedded into Mannex refresher training | Autonomous Maintenance | Identify Pilot Machines for autonomous maintenance
|  | Mannex to initially drive RCA then gradually suppport at deparmental level | Reliabilty/TPM | Review Planned Maintenance schedule to run time instead of calender time
| OEE | Clear capturing of Metrics and KPI
Target setting for OEE and KPI Improvement
| Reliabilty/TPM | Reduce unplanned downtime; review historical downtime data for 2 years, narrow down key 20% and develop action plan |  | Review the Q1 unplanned Downtime and check for improvement if positive move on to the next 20% develop action plan
Reduce Rework; Identify QCPs and Monitor
Track Predictive Maintenance compliance
| Capability development | Introduction to Manufacturing Excellence Refresher training(RCA,5S, KPI visual management and Metrics etc) for all operations staff | Capabilty Training | Develop Capabality Matrix for production and Quality team
|  | Leadership Training |  | Autonomous Maintenance Training